## Slide 1
PROJECT PLAN
2-Sprint
Delivery
Roadmap
START
Apr 28, 2026
END
May 22, 2026
DURATION
2 Sprints / 4 Weeks
TASKS
8 Deliverables
Owner: Engineering & Release Mgmt
Sprint Timeline
Two-week sprints • Sequential & parallel workstreams
SPRINT 1 • Apr 28 – May 8
SPRINT 2 • May 11 – May 22
WEEK 1
WEEK 2
WEEK 3
WEEK 4
1
Generate deterministic code
Dev Team
5 days
2
Update & add required tools
Dev / Platform
5 days
3
Code validation & testing
QA / Dev
4 days
4
UAT deployment & sign-off
QA / Business
4 days
5
Approvals
Stakeholders
2 days
6
Production package ready
Release Mgmt
2 days
7
Lock CR
Change Mgmt
1 day
8
Execute CR
Release Mgmt
3 days
Build & Validate
UAT & Approval
Production CR
★ Go-Live: May 22, 2026